## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Keerthi | 2025-11-26 | Microphone input capturing background noise | Sprint 1 | Keerthi | Logical | Applied noise filtering and tested in quiet environment | 2025-11-27 | Closed | Issue resolved after audio preprocessing
2 | Keerthi | 2025-11-29 | Video audio extraction failed for some formats | Sprint 1 | Keerthi | Logical | Added format validation and conversion logic | 2025-11-30 | Closed | Supports common video formats now
3 | Keerthi | 2025-12-03 | Incorrect language detection in some speech samples | Sprint 2 | Keerthi | Logical | Tuned Whisper parameters and retested inputs | 2025-12-04 | Closed | Improved translation accuracy
4 | Keerthi | 2025-12-06 | Delay in text-to-speech audio generation | Sprint 2 | Keerthi | Maintainability | Optimized TTS configuration | 2025-12-07 | Closed | Reduced response time
5 | Keerthi | 2025-12-10 | UI alignment issue on different screen sizes | Sprint 3 | Keerthi | User Interface | Adjusted layout and CSS responsiveness | 2025-12-11 | Closed | UI now responsive
6 | Keerthi | 2025-12-12 | Minor bugs during final testing | Sprint 3 | Keerthi | Logical | Debugged and performed regression testing | 2025-12-13 | Closed | System stabilized

## Sheet2
Logical
User Interface
Maintainability
Standards
Others